## Tabelle1
genometa project overview
Functional requirements |  |  |  | status | assigned protocol # | pct done
Priority 1 | 1.1 | Graphs |  | started
|  |  | optically pleasing |  | 27, 28, 35, 40, 45, 46, 47, 52, 53, 63, 64, 65, 70 | 80%
|  |  | editable |  |  | 80%
| 1.2 | Summary of all species |  | started
|  |  | show bacteria names |  |  | 0%
|  |  | show summed read hits |  | 48, 49, 66, 67 | 50%
|  |  | summed reads in left hand widget |  | 36, 76 | 10%
| 1.3 | Reads aligned to one species |  | started
|  |  | show read positions |  |  | 50%
| 1.4 | Zoomable Graphs |  | started
|  |  | show complete histogram |  | 71, 72, 73, 74, 81, 82 | 90%
|  |  | multiple zoom levels |  | 39 | 90%
Priority 2 | 2.1 | Feature annotation track (GFF file) |  | started
|  |  | display genes at their positions |  | 84 | 90%
|  |  | stack overlapping genes |  |  | 100%
| 2.2 | Map RefSeq to species name |  | started
|  |  | display RefSeq and name |  | 61, 75, 83, 85 | 90%
| 2.3 | Map genera name to lineage name |  | not started
|  |  | display lineage name |  |  | 0%
| 2.4 | Text Export |  | not started
|  |  | export information to csv format |  |  | 0%
| 2.5 | Analyze number of reads |  | not started
|  |  | show number of reads in info widget |  |  | 0%
|  |  | transcriptonics/metagenomics distinction |  |  | 0%
Priority 3 | 3.1 | Run external aligner |  | started
|  |  | bowtie |  | 16, 24, 68 | 30%
Priority 4 | 4.1 | Sequence Export |  | not started
|  |  | export sequence to text |  |  | 0%
| 4.2 | Graph Export |  | discussion
|  |  | export graphs to vector format |  |  | 75%
|  |  | export graphs to raster format |  |  | 75%
| 4.3 | Transcriptome analysis |  | not started
|  |  | list coordinates of possible sRNAs or ORFs |  |  | 0%
Priority 5 | 5.1 | SNP visualisation |  | not started
|  |  | mismatches should be flagged and vis. |  |  | 0%
Non-functional requirements
Priority 1 | 1.1 | Usability |  | started
|  |  | clear und understandable menu system |  | 29, 37, 43 | 75%
|  |  | installation guide |  |  | 0%
| 1.2 | Memory efficiency |  | started
|  |  | fast SAM/BAM importer/parser |  | 10, 18, 22, 23, 30, 33 | 80%
|  |  | show current memory usage |  |  | 100%
| 1.3 | Multi processor capable |  | not started
|  |  | parallelized |  |  | 0%
| 1.4 | Documentation |  | started
|  |  | document source code |  | 20, 21 | 100%
|  |  | how to |  |  | 0%
|  |  | tips and tricks |  |  | 0%
| 1.5 | Programming language |  | finished
|  |  | Java |  |  | 100%
|  |  | external libraries documented |  |  | 100%
Priority 2 | 2.1 | Platform independence |  | started
|  |  | platform specific installer |  |  | 90%
|  |  | well organized and packaged |  | 11, 12, 20, 21 | 100%
| 2.2 | Website |  | not started
|  |  | create simple website |  |  | 0%
| 2.3 | Open Source
|  |  | make source code available | started | 17, 58, 59, 79, 80 | 75%